## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | DATA SCIENCE PROJECT
PROJECT SPONSOR | CLOUD COUNSELAGE Pvt LTD
PROJECT MANAGER | JAYANTH G S
EXPECTED START DATE | 2020-06-15
EXPECTED COMPLETION DATE | 2020-07-31
ESTIMATED COST | FREE
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | To find best model for data classification and visualising data for finding insights in dataset
BUSINESS CASE | company can improve intern recruitement process and make better decision regarding internship program
GOALS/METRICS | A meaningful data visualization model for data set, a highly accurate classifier for segmenting the eligible and not eligible students
EXPECTED DELIVERABLES | Identify classification model with high accuracy
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | Binary classifier to classify if interns are eligible for internship or not
OUTSIDE OF SCOPE | Use by other educational institutes for hiring interns
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Ashutosh Gulame
SUPPORT RESOURCES | Laptop,Internet
SPECIAL NEEDS | None
PROJECT BENEFITS AND CUSTOMERS
PROCESS OWNER | Ashutosh Gulame
KEY STAKEHOLDERS | Jayanth G S, Nirbhey Singh Pahwa
END CUSTOMER | Cloud couselage Pvt.Ltd
EXPECTED BENEFIT | Better recruitment next time which leads to better quality of interns.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | Dataset might contain low quality data,Unclean data, Sample data may not be true representative of the population
ASSUMPTIONS | Dataset is reliable, analysis does not have mistakes.
CONSTRAINTS | short time for project completion