## RAID LOG
| RAID Log | [9 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 7 | 0 | 1 | 0 | 0 | 0
| Project title: | DATA SCIENCE PROJECT |  | Project Id: |  | Project Manager: | JAYANTH G S |  |  | Assumption | 1 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 1 | 0 | 0 | 0 | 0 | 0
|  |  |  | Last Updated date: | 2020-07-30 | Project Team Lead: | Ashutosh Gulame |  |  | Dependency | 1 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 10 |  |  |  |  | 1
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
3 | Assumption | Data is correct | we can work without any doubt | Check with the source | CLOUD COUNSELAGE | High |  | Closed | Issue
4 | Risk | Worthy candidate misses out and not so worthy can get the internship | Work done by the person gets affetcted,thereby affecting company. | Interview the selected candidates if possible | CLOUD COUNSELAGE | High |  | Open | Dependency
5 | Risk | Training of model not proper | Accuracy of result wont be achieved | Research well and follow a proper methodology | Ashutosh Gulame | Critical |  | Closed
6 | Risk | Cleaning of data isnt done proper | Preprocessing will have errors. | Look at the dataset properly and understand it well so that its cleaned properly | Ashutosh Gulame | Moderate |  | Closed | Open
7 | Risk | Other members code | No impact as its individual work | Don’t look at them | Ashutosh Gulame | Negligible |  | Closed | Closed
8 | Risk | Data breach | candidate selection is affected | keep your product secure | Ashutosh Gulame | Critical |  | Closed
9 | Risk | Improper Working Conditions | Project wont end on time | Provide adequate help and working conditions | CLOUD COUNSELAGE | Moderate |  | Closed | Critical
10 | issue | choosing correct algorithm | bad algoritm affect accuracy | Make sure to find right algorithm | Ashutosh Gulame | Low |  | Closed | High
11 | Dependency | Accuracy of model | Wont predict accurate results | Train and tune model properly | Ashutosh Gulame | High |  | Closed | Moderate
12 | Risk | Laptop not working | Cannot do coding | repair the laptop as soon as possible | Ashutosh Gulame | Critical |  | Closed | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24